## EMA Plan
EMA Plan
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Current Day: | 18 |  |  | Planned Duration | [5 empty] | To-do (scheduled) |  |  |  |  | Completed |  |  |  |  | To-do (outside schedule) | [7 empty] | Completed (outside schedule)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | DAYS | [26 empty] | T217 Workplan | [11 empty] | T217 TMA05 |  | M250 TMA05 | [27 empty] | T217
[34 empty] | Deadline | [11 empty] | Deadline |  | Deadline | [27 empty] | EMA Deadline
[7 empty] | 29/03 | 30/03 | 31/03 | 01/04 | 02/04 | 03/04 | 04/04 | 05/04 | 06/04 | 07/04 | 08/04 | 09/04 | 10/04 | 11/04 | 12/04 | 13/04 | 14/04 | 15/04 | 16/04 | 17/04 | 18/04 | 19/04 | 20/04 | 21/04 | 22/04 | 23/04 | 24/04 | 25/04 | 26/04 | 27/04 | 28/04 | 29/04 | 30/04 | 01/05 | 02/05 | 03/05 | 04/05 | 05/05 | 06/05 | 07/05 | 08/05 | 09/05 | 10/05 | 11/05 | 12/05 | 13/05 | 14/05 | 15/05 | 16/05 | 17/05 | 18/05 | 19/05 | 20/05 | 21/05 | 22/05 | 23/05 | 24/05 | 25/05 | 26/05 | 27/05 | 28/05 | 29/05 | 30/05 | 31/05 | 01/06 | 02/06 | 03/06 | 04/06 | 05/06 | 06/06
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
· | Review and re-read relevant materials | 1 | 7 | 1 | 7 | 100%
| · Review relevant OU materials and past TMAs | 1 | 7 | 1 | 7 | 100%
| · Read EMA documentation, understand requirements, take notes (returning to above) | 1 | 7 | 1 | 7 | 100%
· | Create project plan | 8 | 14 | 8 | 11 | 100%
| · Prepare activity schedule | 8 | 7 | 8 | 5 | 100%
| (a) Come up with required activities and ideas | 8 | 2 | 8 | 2 | 100%
| (b) Decide suitable activity timeframes | 10 | 1 | 9 | 1 | 100%
| (c) Finalize and implement into Excel chart | 11 | 4 | 10 | 3 | 100%
| · Prepare risk assessment | 15 | 6 | 13 | 5 | 100%
| (a) Come up with possible risks and check schedule | 15 | 3 | 13 | 2 | 100%
| (b) Analyze each risk and their mitigations | 18 | 2 | 15 | 2 | 100%
| (c) Edit and compile into table | 20 | 1 | 17 | 1 | 100%
| · Prepare the final Workplan document | 21 | 1 | 18 | 1 | 100%
· | Review document(s) against requirements, edit, then submit final EMA Workplan | 22 | 1 | 18 | 1 | 100%
· | Implement version control | 25 | 1
| · Download files and set up repository using Github | 25 | 1
| · Commit initial project files to repository | 25 | 1
| · Periodically commit changes to repository | 25 | 31
| · Ensure repository structure and documentation is clear | 25 | 31
· | Perform further research on navigable wireframes as needed | 26 | 12 |  |  | 100%
· | Create navigable wireframes | 26 | 10 |  |  | 100%
| · Review requirements for the admin application | 26 | 1 |  |  | 100%
| · Experiment with wireframe layouts for desktops using Figma | 26 | 7 |  |  | 100%
| · Evaluate and select the most suitable design | 33 | 2
| · Finalize the selected wireframe and adapt it to various screen sizes (laptop, tabet, mobile) | 35 | 1
| · Test the wireframes against the requirements | 35 | 1
· | Explain wireframes and design choices, documenting: | 36 | 2
| · The wireframes themselves | 36 | 1
| · The purpose and significance of wireframes | 36 | 1
| · The requirements and so design choice(s) | 36 | 2
· | Perform further research on responsivity as needed | 38 | 10
· | Create 'Add Club Ride' page | 38 | 5
| · Create a structure for the page using HTML | 38 | 1
| · Style the page like the wireframe with CSS | 38 | 1
| · Create media queries in CSS for responsiveness | 39 | 1
| · Implement form functionality | 40 | 3
| · Test and evaluate the site usability, accessibility & function (on various screen sizes) | 43 | 2
| · Validate HTML and CSS using W3C tools | 45 | 1
· | Document: | 46 | 2
| · The code for 'Add Club Ride' page | 46 | 1
| · The purpose and principles of responsive design | 46 | 1
| · The adoption of 'Add Club Ride' page to mobile | 47 | 1
| · Evaluation of 'Add Club Ride' page for mobile with any (i) compromises and (ii) future recommendations | 47 | 1
· | Conduct research on future developments | 48 | 4
| · Write up on 'Ensuring System Availability' | 48 | 2
| (a) Research system availability topic as needed | 48 | 2
| (b) Identify and document availability requirements | 48 | 1
| (c) Propose and recommend solutions | 49 | 1
| · Write up on 'Mobile Sensor Integration' | 50 | 2
| (a) Research sensors and their potential benefits | 50 | 2
| (b) Find relevant sensors for integration | 50 | 1
| (c) Assess security risks and mitigation strategies | 51 | 1
| (d) Provide possible recommendations | 51 | 1
· | Develop acceptance tests | 52 | 3
| · Look at best practices and requirements if needed | 52 | 3
| · Create acceptance tests for 'good' and 'bad' inputs | 52 | 1
| · Repeat above for adding announcements functionality | 52 | 1
| · Compile acceptance tests & results in table | 53 | 2
· | Research and refer to version control documents as needed | 55 | 1
· | Write up version control section | 55 | 1
| · Define version control and its purpose | 55 | 1
| · Explain benefits of version control | 55 | 1
| · Document version control strategy used | 55 | 1
| · Capture screenshots as evidence, embed them | 55 | 1
· | Reflect on EMA (and document all the below) | 56 | 3
| · Evaluate effectiveness of planning processes | 56 | 1
| · Assess use and effectiveness of work plan (part 1) | 56 | 1
| · Analyze impact of planning on EMA | 57 | 2
| · Extract key lessons learned for future | 58 | 1
· | Review documentation and work done against requirements, edit, and submit the final EMA | 59 | 2

## EMA Risks
Event | Likelihood | Impact | Risk | Mitigation(s)
Misinterpreting EMA requirements or expectations | Low | High | Medium | Thoroughly read and think about the EMA, ask for clarifications from my tutor if necessary, review requirements against the work multiple times.
Possible need for extra time (e.g. to research, code, write up the report, etc.) | Medium | High | High | Plan buffer time in the schedule, prioritize tasks effectively, keep track of progress.
Inability to find the necessary research materials or reference | High | Medium | High | Start the EMA ahead of schedule with buffer time, use various sources and methods of gathering information, ask tutors if necessary.
Potential technical issues with any of the used software/tools | Medium | High | High | Keep software/tools up to date, troubleshoot issues immediately and, if necessary, look for solutions in online forums or tech support.
Inconsistencies or bugs in responsive design across different devices | Medium | High | High | Test on various devices, use responsive design best practices and look for solutions in online forums or tech support.
Risk of prolonged internet outages | Low | Medium | Low | Have local backups of the course materials and TMA files e.g. in the case of outages.
Version control issues, e.g. code merge conflicts | Medium | High | High | Communicate changes effectively with team members, use version control tools effectively, resolve conflicts promptly.
Overlapping submission dates for other OU modules (both TMA05s marked on the plan) | Medium | High | High | Plan and prioritize tasks across modules, communicate with tutors for possible extensions if needed.
Failures in code after test with no apparent fix | Medium | High | High | Implement thorough testing procedures, seek assistance from online communities or tutors, refactor code if necessary.
Limited proficiency or knowledge with Figma (first time creating) | High | Medium | High | Regularly review my work, watch and learn from tutorials and other online resources to improve prior to real EMA work, ask for feedback from my friends/family.
Sudden changes to the EMA description | Low | Medium | Low | Stay updated with OU notifications and forums, check my emails regularly, quickly adjust plans accordingly.
Risk of computer hardware failure (eg, SSD failure) | Low | High | Medium | Regularly backup work in my local storage (but also pCloud drive, where my work is mainly - I use the desktop application so it functions like physical storage), invest in reliable hardware, anticipate potential hardware issues.
Early mistakes leading to subsequent errors and huge time loss | Medium | High | High | Always check work for errors and possible optimizations, break tasks into smaller steps to catch mistakes early, seek feedback from peers.
Difficulty in understanding user needs or requirements | Medium | High | High | Consult the module materials or other resources on any unclear points, check other students' thoughts in the OU forum and seek guidance from tutors if needed.
Potential compatibility issues with software or platforms | Medium | High | High | Research compatibility and software requirements beforehand, test it early, have contingency plans.
Unforeseen external events (eg, illness, family emergencies) | Low | High | Medium | Communicate early with tutors about any sudden events or possible disruptions to the work, plan tasks with buffer time for unexpected situations.
Human errors (e.g, failure to save files, misplacing photos) | Medium | Medium | Medium | Develop a file organization system, regularly save work, backup important files, double-check file locations, be sure to think properly.
External pressure or distractions affecting focus and productivity | High | Medium | High | Keep a focused workspace, set self-rules or control settings if necessary, practice time management techniques, seek support if needed.
Plagiarism or improper citation of sources | Low | High | Medium | Strictly adhere to proper citation and referencing guidelines, and keep track of all sources in the references section (even if not fully referenced yet)